## W01
PROJECT REPORT
Group | <QNP>
Week | <09/05/2022-15/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Divide Task | Completed | Each members in team has responsibility for at least 1 document
2 | Analysing Requirements | Completed | Depend on the context part of the project, so that make a list of requirements
3 | Write SRS Part I | Completed
4 | Push project into Github | Completed | Each members in team can access to the project through Github
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Write Weekly Report | PhucLH
2 | Write introduction of SRS | NhanND
3 | Design Diagram | QuanTM
4 | Design Screen Flow | PhucTH
5 | Design Screen Details | QuanVT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Analysing Requirements | In Progress
2 | Design Diagram clearly | In Progress | References to text book
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Documents | 2022-05-15
2 | Create project in github | 2022-05-15
3 | Research deloy project on the web | 2022-05-15
4 | Create task in jira | 2022-05-15
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Use tailwindcss in project | QuanVT
2 | Use Nextjs, Reactjs in project | NhanND
3 | Suggest MySql | PhucLH
4 | Back-end use Nodejs | QuanTM
5 | Use MongDB | PhucTH

## W02
PROJECT REPORT
Group | QNP
Week | 16/05/2022-22/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Fix problem in SRS | In Progress | Introduction, Screen flow, Context Diagram, System Function
2 | Search Web Scheleton | In Progress | https://themewagon.com/themes/free-modern-bootstrap-4-html5-travel-website-template-pacific/
3 | Work in SRS part II Functional Requirements | In Progress
4 | Update working schedule | In Progress
5 | Work with Backlog document | In Progress
6 | Design ERD | In Progress
7 | Design Mockup (Wireframe) depends on screen flow | In Progress
8 | Design UI | In Progress
9 | Weekly Report | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design ERD | NhanND
2 | Design Mockup (Wireframe) | PhucLH
3 | Work with Backlog | QuanTM
4 | Search Web Scheleton | PhucLH
5 | Fix Screen Flow | PhucTH
6 | Design UI | QuanVT
7 | Work in SRS part II | Whole Team
8 | Weekly Report | PhucLH
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in ERD | In Progress
2 | Fix trouble in SRS | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-05-22
2 | Work on SDD | 2022-05-22
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W03
PROJECT REPORT
Group | QNP
Week | 23/05/2022-29/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work with Backlog document | In Progress
5 | Design Mockup (Wireframe) depends on screen flow | In Progress
6 | Work in Iteration 1 | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design ERD | NhanND
2 | Design Mockup (Wireframe) | PhucLH
3 | Work with Backlog | QuanTM
4 | Design UI | QuanVT
5 | Work in iteration 1 | Team | Depends on Backlog Document
6 | Weekly Report | PhucLH
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in ERD | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-05-29
2 | Work on SDD | 2022-05-29
3 | Continue work with integration 1 | 2022-05-29
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W04
PROJECT REPORT
Group | QNP
Week | 30/05/2022-06/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work SRS part II | In Progress
5 | Design Mockup (Wireframe) depends on screen flow | In Progress
6 | Work in Itegration 1 | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design ERD | NhanND
2 | Design Mockup (Wireframe) | PhucLH
3 | Work with Backlog | QuanTM
4 | Design UI | QuanVT
5 | Work in itegration 1 | Team | Depends on Backlog Document
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in ERD | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-06-06
2 | Work on SDD | 2022-06-06
3 | Continue work with integration 1 | 2022-06-06
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W05
PROJECT REPORT
Group | QNP
Week | 7/06/2022-13/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work SRS part II | In Progress
5 | Design Mockup (Wireframe) depends on screen flow | In Progress
6 | Work in Itegration 1 | In Progress
7 | Write Core Workflow | In Progress
8 | Teamwork off-class | In Progress
9 | Fix code structure | In Progress
10 | Build complete function | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design ERD | NhanND
2 | Design Mockup (Wireframe) | PhucLH
3 | Work with Backlog | QuanTM
4 | Design UI | QuanVT
5 | Work in integration 1 | Team | Depends on Backlog Document
6 | Write core workflow | QuanVT
7 | Working on Itegration 2 | Team
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in code structure | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-06-13
2 | Work on SDD | 2022-06-13
3 | Continue work with integration 2 | 2022-06-13
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W06
PROJECT REPORT
Group | QNP
Week | 13/06/2022-20/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work SDD | In Progress
5 | Write Core Workflow | In Progress
6 | Teamwork off-class | In Progress
7 | Fix code structure | In Progress
8 | Build complete function | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Feature belong to Field | NhanND
2 | Code Feature belong to Admin | PhucLH
3 | Code Feature belong to Booking | QuanTM
4 | Design UI | QuanVT
5 | Work in SDD | Team | Depends on Backlog Document
6 | Code Feature belong to user | QuanVT
7 | Code Feedback and Forgot Password | PhucTH
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in code structure | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-06-20
2 | Work on SDD | 2022-06-20
3 | Continue work with integration 2-3 | 2022-06-20
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W07
PROJECT REPORT
Group | QNP
Week | 21/06/2022-27/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work SDD | In Progress
5 | Write Core Workflow | In Progress
6 | Teamwork off-class | In Progress
7 | Fix code structure | In Progress
8 | Build complete function | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Feature belong to Field | NhanND
2 | Code Feature belong to Admin | PhucLH
3 | Code Feature belong to Booking | QuanTM
4 | Design UI | QuanVT
5 | Work in SDD | Team | Depends on Backlog Document
6 | Code Feature belong to user | QuanVT
7 | Code Feedback and Forgot Password | PhucTH
8 | Paging | PhucLH
9 | implement Booking Calendar | NhanND
10 | implement Booking Field | QuanVT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in code structure | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-06-27
2 | Work on SDD | 2022-06-27
3 | Continue work with integration 2-3 | 2022-06-27
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W08
PROJECT REPORT
Group | QNP
Week | 28/06/2022-04/07/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work SDD | In Progress
5 | Write Core Workflow | In Progress
6 | Teamwork off-class | In Progress
7 | Fix code structure | In Progress
8 | Build complete function | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Feature belong to Field | NhanND
2 | Code Feature belong to Admin | PhucLH
3 | Code Feature belong to Booking | QuanTM
4 | Design UI | QuanVT
5 | Work in SDD | Team | Depends on Backlog Document
6 | Code Feature belong to user | QuanVT
7 | Code Feedback and Forgot Password | PhucTH
8 | Paging | PhucLH
9 | implement Booking Calendar | NhanND
10 | implement Booking Field | QuanVT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in code structure | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-07-04
2 | Work on SDD | 2022-07-04
3 | Continue work with integration 3 | 2022-07-04
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W09
PROJECT REPORT
Group | QNP
Week | 5/07/2022-11/07/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work SDD | In Progress
5 | Write Core Workflow | In Progress
6 | Teamwork off-class | In Progress
7 | Fix code structure | In Progress
8 | Build complete function | In Progress
9 | Finish SDD | In Progress | About code design
10 | Validation Project | In Progress | Show announcement when user input or do something
11 | Complete Booking function | In Progress | Booking many slots in many days in 1 time
12 | Improve performance of project | In Progress | Fix sql query
13 | Clean code | In Progress | Delete unused import, format code
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Feature belong to Field | NhanND
2 | Code Feature belong to Admin | PhucLH
3 | Code Feature belong to Booking | QuanTM
4 | Design UI | QuanVT
5 | Work in SDD | Team | Depends on Backlog Document
6 | Code Feature belong to user | QuanVT
7 | Code Feedback and Forgot Password | PhucTH
8 | Paging | PhucLH
9 | implement Booking Calendar | NhanND
10 | implement Booking Field | QuanVT
11 | improve performance | QuanTM
12 | Clean code | PhucTH
13 | Validation project | Team | Team members validation their code depends on task of them
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in code structure | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-07-11
2 | Work on SDD | 2022-07-11
3 | Continue work with integration 3 | 2022-07-11
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W10
PROJECT REPORT
Group | QNP
Week | 12/07/2022-18/07/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work SDD | In Progress
5 | Write Core Workflow | In Progress
6 | Teamwork off-class | In Progress
7 | Fix code structure | In Progress
8 | Build complete function | In Progress
9 | Finish SDD | In Progress | About code design
10 | Validation Project | In Progress | Show announcement when user input or do something
11 | Complete Booking function | In Progress | Booking many slots in many days in 1 time
12 | Improve performance of project | In Progress | Fix sql query
13 | Clean code | In Progress | Delete unused import, format code
14 | Design powerpoint | In Progress | About main core flow of the project
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Code Feature belong to Field | NhanND
2 | Code Feature belong to Admin | PhucLH
3 | Code Feature belong to Booking | QuanTM
4 | Design UI | QuanVT
5 | Work in SDD | Team | Depends on Backlog Document
6 | Code Feature belong to user | QuanVT
7 | Code Feedback and Forgot Password | PhucTH
8 | Paging | PhucLH
9 | implement Booking Calendar | NhanND
10 | implement Booking Field | QuanVT
11 | improve performance | QuanTM
12 | Clean code | PhucTH
13 | Validation project | Team | Team members validation their code depends on task of them
14 | Design Powerpoint | PhucLH
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in code structure | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-07-17
2 | Work on SDD | 2022-07-17
3 | Continue work with integration 3 | 2022-07-17
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes