## W01
PROJECT REPORT
Group | <QNP>
Week | <09/05/2022-15/05/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Divide Task | Completed | Each members in team has responsibility for at least 1 document
2 | Analysing Requirements | Completed | Depend on the context part of the project, so that make a list of requirements
3 | Write SRS Part I | Completed
4 | Push project into Github | Completed | Each members in team can access to the project through Github
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Write Weekly Report | PhucLH
2 | Write introduction of SRS | NhanND
3 | Design Diagram | QuanTM
4 | Design Screen Flow | PhucTH
5 | Design Screen Details | QuanVT
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Analysing Requirements | In Progress
2 | Design Diagram clearly | In Progress | References to text book
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Documents | 2022-05-22
2 | Create project in github | 2022-05-22
3 | Research deloy project on the web | 2022-05-22
4 | Create task in jira | 2022-05-22
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
1 | Use tailwindcss in project | QuanVT
2 | Use Nextjs, Reactjs in project | NhanND
3 | Suggest MySql | PhucLH
4 | Back-end use Nodejs | QuanTM
5 | Use MongDB | PhucTH

## W02
PROJECT REPORT
Group | QNP
Week | 16/05/2022-22/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Fix problem in SRS | In Progress | Introduction, Screen flow, Context Diagram, System Function
2 | Search Web Scheleton | In Progress | https://themewagon.com/themes/free-modern-bootstrap-4-html5-travel-website-template-pacific/
3 | Work in SRS part II Functional Requirements | In Progress
4 | Update working schedule | In Progress
5 | Work with Backlog document | In Progress
6 | Design ERD | In Progress
7 | Design Mockup (Wireframe) depends on screen flow | In Progress
8 | Design UI | In Progress
9 | Weekly Report | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design ERD | NhanND
2 | Design Mockup (Wireframe) | PhucLH
3 | Work with Backlog | QuanTM
4 | Search Web Scheleton | PhucLH
5 | Fix Screen Flow | PhucTH
6 | Design UI | QuanVT
7 | Work in SRS part II | Whole Team
8 | Weekly Report | PhucLH
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in ERD | In Progress
2 | Fix trouble in SRS | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-05-30
2 | Work on SDD | 2022-05-30
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W03
PROJECT REPORT
Group | QNP
Week | 23/05/2022-29/05/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work with Backlog document | In Progress
5 | Design Mockup (Wireframe) depends on screen flow | In Progress
6 | Work in Iteration 1 | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design ERD | NhanND
2 | Design Mockup (Wireframe) | PhucLH
3 | Work with Backlog | QuanTM
4 | Design UI | QuanVT
5 | Work in iteration 1 | Team | Depends on Backlog Document
6 | Weekly Report | PhucLH
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in ERD | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-06-06
2 | Work on SDD | 2022-06-06
3 | Continue work with integration 1 | 2022-06-06
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W04
PROJECT REPORT
Group | QNP
Week | 30/05/2022-06/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work SRS part II | In Progress
5 | Design Mockup (Wireframe) depends on screen flow | In Progress
6 | Work in Itegration 1 | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design ERD | NhanND
2 | Design Mockup (Wireframe) | PhucLH
3 | Work with Backlog | QuanTM
4 | Design UI | QuanVT
5 | Work in itegration 1 | Team | Depends on Backlog Document
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in ERD | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-06-06
2 | Work on SDD | 2022-06-06
3 | Continue work with integration 1 | 2022-06-06
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes

## W05
PROJECT REPORT
Group | QNP
Week | 30/05/2022-06/06/2022
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Weekly Report | In Progress
2 | Work with SDD | In Progress
3 | Update working schedule | In Progress
4 | Work SRS part II | In Progress
5 | Design Mockup (Wireframe) depends on screen flow | In Progress
6 | Work in Itegration 1 | In Progress
7 | Write Core Workflow | In Progress
8 | Teamwork off-class | In Progress
9 | Fix code structure | In Progress
10 | Build complete function | In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Design ERD | NhanND
2 | Design Mockup (Wireframe) | PhucLH
3 | Work with Backlog | QuanTM
4 | Design UI | QuanVT
5 | Work in integration 1 | Team | Depends on Backlog Document
6 | Write core workflow | QuanVT
7 | Working on Itegration 2 | Team
III. Project Issues
# | Project Issue | Status | Notes (Solution, Suggestion, etc.)
1 | Fix trouble in code structure | In Progress
2 | Fix trouble in SRS | In Progress
3 | Fix trouble in SDD | In Progress
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
1 | Finish Document | 2022-06-06
2 | Work on SDD | 2022-06-06
3 | Continue work with integration 1 | 2022-06-06
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes