## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
| Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
1 | View contact information | View contact information | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
2 | View home page | View landing page | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
3 | Profile of user | View account’s profile | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
4 | Update profile of user | View account’s profile | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
5 | Login (google) | Authentication | Medium | Iteration 1 | SE150983 | Trần Hữu Phúc | Iteration 2
6 | Create account for Customer | Sign up account | Simple | Iteration 1 | SE150983 | Trần Hữu Phúc | Iteration 2
7 | Forgot Password | Reset password | Simple | Iteration 1 | SE150983 | Trần Hữu Phúc | Iteration 3
8 | Change password | Reset password | Simple | Iteration 3 | SE150983 | Trần Hữu Phúc | Iteration 3
9 | View admin page | View admin page | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
10 | Delete account | Manage list of accounts | Simple | Iteration 1 | SE150989 | Lê Hoàng Phúc | Iteration 2
11 | Search account | Manage list of accounts | Medium | Iteration 1 | SE150989 | Lê Hoàng Phúc | Iteration 2
12 | Update account | Manage list of accounts | Simple | Iteration 1 | SE150989 | Lê Hoàng Phúc | Iteration 2
13 | Update Field | Manage list of fields | Simple | Iteration 1 | SE150954 | Nguyễn Đức Nhân | Iteration 2
14 | View information detail of Field | Manage owner’s field detail | Simple | Iteration 2 | SE150954 | Nguyễn Đức Nhân | Iteration 3
15 | Search Field | Manage list of fields | Medium | Iteration 1 | SE150954 | Nguyễn Đức Nhân | Iteration 2
16 | Delete Field | Manage list of fields | Simple | Iteration 1 | SE150954 | Nguyễn Đức Nhân | Iteration 2
17 | Create information of new Field | Create new field | Simple | Iteration 2 | SE150954 | Nguyễn Đức Nhân | Iteration 3
18 | Search info history Booking field | Manage Booking field | Medium | Iteration 1 | SE151001 | Trần Minh Quân | Iteration 3
19 | View detail info history booking | Manage Booking field | Simple | Iteration 1 | SE151001 | Trần Minh Quân | Iteration 3
20 | Update booked field of owner's field | View booking history of owner’s field | Medium | Iteration 3 | SE151001 | Trần Minh Quân | Iteration 3
21 | Delete booked field of owner's field | View booking history of owner’s field | Simple | Iteration 3 | SE151001 | Trần Minh Quân | Iteration 3
22 | View income of all order | View booking history of owner’s field | Medium | Iteration 3 | SE151001 | Trần Minh Quân | Final
23 | View Similar Field | View field detail | Simple | Iteration 2 | SE151000 | Võ Trung Quân | Iteration 3
24 | View Booking Field of customer | Booking field | Simple | Iteration 2 | SE151001 | Trần Minh Quân | Iteration 3
25 | Update Booking Field of customer | Booking field | Simple | Iteration 2 | SE151001 | Trần Minh Quân | Iteration 3
26 | Delete Booking Field of customer | Booking field | Simple | Iteration 2 | SE151001 | Trần Minh Quân | Iteration 3
27 | View QR code | Pay money | Complex | Iteration 2 | SE151000 | Võ Trung Quân | Iteration 3
28 | Check out | Pay money | Simple | Iteration 2 | SE151000 | Võ Trung Quân | Iteration 3
29 | View all booking history of customer | View history of booking | Simple | Iteration 2 | SE151001 | Trần Minh Quân | Iteration 3
30 | Search booking history of customer | View history of booking | Simple | Iteration 2 | SE151001 | Trần Minh Quân | Iteration 3
31 | View detail booked fields of customer | View detail history of booking | Simple | Iteration 2 | SE151001 | Trần Minh Quân | Iteration 3
32 | Search food | Manage food | Medium | Iteration 3 | SE150989 | Lê Hoàng Phúc | Iteration 3
33 | Delete food | Manage food detail | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Iteration 3
34 | View food detail | Manage food detail | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Iteration 3
35 | Update food | Manage food detail | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Iteration 3
36 | Create food | Create new foods | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Iteration 3
37 | Create slot of field | Create new slot | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
38 | Update slot of field | Manage slot of Field | Simple | Iteration 3 | SE151001 | Trần Minh Quân | Iteration 3
39 | Delete slot of field | Manage slot of Field | Simple | Iteration 3 | SE151001 | Trần Minh Quân | Iteration 3
40 | Search slot of field | Manage slot of Field | Medium | Iteration 3 | SE151001 | Trần Minh Quân | Iteration 3
41 | Create category of field | Create field category | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
42 | Search category of field | Manage field category | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
43 | Delete category of field | Manage field category | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
44 | Update category of field | Manage field category | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
45 | Create category of food | Create food category | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Iteration 3
46 | Search category of food | Manage food category | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Iteration 3
47 | Delete category of food | Manage food category | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Iteration 3
48 | Update category of food | Manage food category | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Iteration 3
49 | Create role | Create new role | Simple | Iteration 3 | SE151000 | Võ Trung Quân | Iteration 3
50 | Search role | Manage role | Simple | Iteration 3 | SE151000 | Võ Trung Quân | Iteration 3
51 | Delete role | Manage role | Simple | Iteration 3 | SE151000 | Võ Trung Quân | Iteration 3
52 | Update role | Manage role | Simple | Iteration 3 | SE151000 | Võ Trung Quân | Iteration 3
53 | Create city | Create new city | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
54 | Search city | Manage city | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
55 | Delete city | Manage city | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
56 | Update city | Manage city | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
57 | Create location | Create new location | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
58 | Search location | Manage location | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
59 | Delete location | Manage location | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3
60 | Update location | Manage location | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Iteration 3