## Product Backlog
THE APPLICATION DEVELOPMENT PROJECT TOPIC
PRODUCT BACKLOG
| Function Name | Feature | Complexity | Planned Code Iteration | In-charge Roll Number | In-charge Full Name | Actual Code Iteration
1 | View contact information | View contact information | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
2 | View home page | View landing page | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
3 | Profile of user | View account’s profile | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
4 | Update profile of user | View account’s profile | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
5 | Login (google) | Authentication | Medium | Iteration 1 | SE150983 | Trần Hữu Phúc | Iteration 2
6 | Create account for Customer | Sign up account | Simple | Iteration 1 | SE150983 | Trần Hữu Phúc | Iteration 2
7 | Forgot Password | Reset password | Simple | Iteration 1 | SE150983 | Trần Hữu Phúc | Iteration 2
8 | View admin page | View admin page | Simple | Iteration 1 | SE151000 | Võ Trung Quân | Iteration 2
9 | Delete account | Manage list of accounts | Simple | Iteration 1 | SE150989 | Lê Hoàng Phúc | Iteration 2
10 | Search account | Manage list of accounts | Medium | Iteration 1 | SE150989 | Lê Hoàng Phúc | Iteration 3
11 | Update account | Manage list of accounts | Simple | Iteration 1 | SE150989 | Lê Hoàng Phúc | Iteration 2
12 | Update status Field | Manage list of fields | Simple | Iteration 1 | SE150954 | Nguyễn Đức Nhân | Iteration 2
13 | Search Field | Manage list of fields | Medium | Iteration 1 | SE150954 | Nguyễn Đức Nhân | Iteration 2
14 | Delete Field | Manage list of fields | Simple | Iteration 1 | SE150954 | Nguyễn Đức Nhân | Iteration 2
15 | Search info history Booking field | Manage Booking field | Medium | Iteration 1 | SE151001 | Trần Minh Quân | Iteration 3
16 | Detail info history booking | Manage Booking field | Simple | Iteration 1 | SE151001 | Trần Minh Quân | Iteration 3
17 | View Screen Customer | View Screen customer | Simple | Iteration 1 | SE151001 | Trần Minh Quân | Iteration 3
18 | Search Active Field | View list of field | Simple | Iteration 2 | SE151000 | Võ Trung Quân | Iteration 3
19 | View detail of Field | View field detail | Simple | Iteration 2 | SE151000 | Võ Trung Quân | Iteration 3
20 | Feedback | View field detail | Simple | Iteration 2 | SE151000 | Võ Trung Quân | Iteration 3
21 | View Similar Field | View field detail | Simple | Iteration 2 | SE151000 | Võ Trung Quân | Iteration 3
22 | Update Order Field | Booking field | Simple | Iteration 2 | SE150983 | Trần Hữu Phúc | Iteration 3
23 | Delete Order Field | Booking field | Simple | Iteration 2 | SE150983 | Trần Hữu Phúc | Iteration 3
24 | Create information Order Field | Booking field | Simple | Iteration 2 | SE150983 | Trần Hữu Phúc | Iteration 3
25 | Booking confirm | Booking field | Simple | Iteration 2 | SE150983 | Trần Hữu Phúc | Iteration 3
26 | View QR code | Pay money | Complex | Iteration 2 | SE151000 | Võ Trung Quân | Iteration 3
27 | Check out | Pay money | Simple | Iteration 2 | SE151000 | Võ Trung Quân | Iteration 3
28 | View all Order of customer | View history of booking | Simple | Iteration 2 | SE151001 | Trần Minh Quân | Iteration 3
29 | Search order of customer | View history of booking | Simple | Iteration 2 | SE151001 | Trần Minh Quân | Iteration 3
30 | View detail booked fields | View detail history of booking | Simple | Iteration 2 | SE151001 | Trần Minh Quân | Iteration 3
31 | View list field of Manager | Manage list owner’s field | Simple | Iteration 2 | SE150989 | Lê Hoàng Phúc | Iteration 3
32 | Search field of manager | Manage list owner’s field | Simple | Iteration 2 | SE150989 | Lê Hoàng Phúc | Iteration 3
33 | Sort Field of manager | Manage list owner’s field | Simple | Iteration 2 | SE150989 | Lê Hoàng Phúc | Iteration 3
34 | Delete Field of manager | Manage list owner’s field | Simple | Iteration 2 | SE150989 | Lê Hoàng Phúc | Iteration 3
35 | Create information of new Field | Create new field | Simple | Iteration 2 | SE150954 | Nguyễn Đức Nhân | Iteration 3
36 | View information detail of Field | Manage owner’s field detail | Simple | Iteration 2 | SE150954 | Nguyễn Đức Nhân | Iteration 3
37 | View all booking field of customer | View booking history of owner’s field | Simple | Iteration 2 | SE150954 | Nguyễn Đức Nhân | Iteration 3
38 | Search booked Field | View booking history of owner’s field | Simple | Iteration 2 | SE150954 | Nguyễn Đức Nhân | Iteration 3
39 | Delete Customer Booking | View booking history of owner’s field | Simple | Iteration 3 | SE150983 | Trần Hữu Phúc | Final
40 | View detail booking | View booking history of owner’s field | Simple | Iteration 3 | SE151001 | Trần Minh Quân | Final
41 | Search order | Manage order | Medium | Iteration 3 | SE150983 | Trần Hữu Phúc | Final
42 | Delete Order | Manage order | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Final
43 | Income of all order | Manage order | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Final
44 | Search Food | Manage food | Medium | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Final
45 | Delete Food | Manage food | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Final
46 | View Food | Manage food | Simple | Iteration 3 | SE150954 | Nguyễn Đức Nhân | Final
47 | Update Food | Manage food | Simple | Iteration 3 | SE150989 | Lê Hoàng Phúc | Final
48 | Create Food | Manage food | Simple | Iteration 3 | SE151001 | Trần Minh Quân | Final
49 | Create slot of field | Manage slot of Field | Simple | Iteration 3 | SE151001 | Trần Minh Quân | Final
50 | Update slot of field | Manage slot of Field | Simple | Iteration 3 | SE151001 | Trần Minh Quân | Final
51 | Delete slot of field | Manage slot of Field | Simple | Iteration 3 | SE151000 | Võ Trung Quân | Final
52 | Search slot of field | Manage slot of Field | Medium | Iteration 3 | SE151000 | Võ Trung Quân | Final
53 | Change password | Manage account | Simple | Iteration 3 | SE150983 | Trần Hữu Phúc | Final